## Sheet1
|  | Project #: |  | 19057 |  |  | Tail Number: | 750VX |  |  | Lever Arm |  |  |  | GPS UNITS | TAIL # | START DATE | 2018-01-01
|  | Flight plan name: |  | 19057_BASE, 19057_BRIGHTANGLE |  |  | Flight Date: | 20190930 |  |  |  | X | Y | Z |  |  | END DATE | 2019-12-31
|  |  | Location: | Grand Canyon |  |  | Sensor SN | PRIME- VX |  |  | GPS | -0.13 | -0.011 | -1.522 | Leica | 732JE
|  |  | Pilot: | Aiden, Courtney |  |  | Weather | clear |  |  | IMU | #N/A | #N/A | #N/A | Topcon | 1872H
|  |  | Operator: | Jun | [5 empty] | Base Station |  | ARP | Start | Stop | Trimble | 750VX
2223 S Drake Ave, Suite 200 |  |  | Sensor: | Galaxy | [6 empty] | 0 | 0 | 0 | 0 |  | 750DV
|  |  | Hobbs Time Start: | 4294.7 | [6 empty] | 0 | 0
Huntsville, AL 35805 |  |  | Hobbs Time Stop: | 4300.6 | [6 empty] | 0 | 0 |  |  | Sensor | GPS |  |  | IMU
PH. (256) 971-9991 |  |  | Pre-Static: | 0804~08:09 | [11 empty] | X | Y | Z | X | Y | Z
FX. (256) 971-1154 |  |  | Post-Static: | 14:28~14:33 | [10 empty] | 7123-JE | -0.129 | 0.26 | -1.337 | -0.45 | 0.119 | -0.203
|  |  | Fwd Lap: | [11 empty] | PRIME- DV | 0.342 | -0.157 | -1.22 | 0 | 0 | 0
|  |  | Side Lap | [11 empty] | 7225-VX | -0.201 | 0.348 | -1.379 | -0.45 | 0.159 | -0.169
Line/DIR |  | Start | End | Air Speed | Alt(ft) | # Exp | Light Values | Total Time | Comments or errors while online: | [5 empty] | 33-VX | 0.714 | -0.172 | -1.152 | 0.005 | -0.015 | -0.192
157 | 261 | 8:31 | 8:32 | 119 | 12262 |  |  | 0:01 | Strip001 SA 4
158 | 81 | 8:36 | 8:37 | 126 | 12365 |  |  | 0:01 | Strip002
159 | 261 | 8:40 | 8:42 | 117 | 12627 |  |  | 0:02 | Strip003 | [5 empty] | 7225-JE | -0.22 | 0.18 | -1.4 | -0.45 | 0.159 | -0.169
160 | 81 | 8:46 | 8:50 | 136 | 13539 |  |  | 0:04 | Strip004 missed the initialization line, overspeed, 150 ft min under target alt. | [5 empty] | 7123-VX | -0.19 | -0.01 | -1.54 | -0.45 | 0.119 | -0.203
161 | 261 | 8:56 | 9:03 | 113 | 13855 |  |  | 0:07 | Strip005, Heavy headwind, SA change
194 | 170 | 9:13 | 9:14 | 121 | 12369 |  |  | 0:01 | Strip006 SA 3
193 | 350 | 9:18 | 9:20 | 126 | 13127 |  |  | 0:02 | Strip007
192 | 170 | 9:24 | 9:26 | 130 | 13271 |  |  | 0:02 | Strip008
191 | 350 | 9:29 | 9:31 | 111 | 13761 |  |  | 0:02 | Strip009
190 | 170 | 9:35 | 9:38 | 103 | 137540 |  |  | 0:03 | Strip010
189 | 350 | 9:41 | 9:44 | 119 | 13732 |  |  | 0:03 | Strip011
188 | 170 | 9:48 | 9:51 | 113 | 13764 |  |  | 0:03 | Strip012
187 | 350 | 9:54 | 9:58 | 128 | 14460 |  |  | 0:04 | Strip013
186 | 170 | 10:02 | 10:08 | 103 | 14629 |  |  | 0:06 | Strip014, pilot accidentally flew over the line while making a turn. Strip 015 strong headwind
185 | 350 | 10:12 | 10:18 | 109 | 14515 |  |  | 0:06 | Strip016 missed the initialization line slightly
184 | 170 | 10:21 | 10:28 | 115 | 14449 |  |  | 0:07 | Strip017 entered the initialization line slightly at an angle
183 | 350 | 10:31 | 10:37 | 121 | 14417 |  |  | 0:06 | Strip018
182 | 170 | 10:42 | 10:48 | 111 | 14333 |  |  | 0:06 | Strip019
181 | 350 | 10:52 | 10:57 | 121 | 14381 |  |  | 0:05 | Strip020
180 | 170 | 11:01 | 11:07 | 113 | 14458 |  |  | 0:06 | Strip021
179 | 350 | 11:11 | 11:17 | 117 | 14473 |  |  | 0:06 | Strip022
120 | 81 | 11:27 | 11:28 | 136 | 14040 |  |  | 0:01 | Strip023, Crossline for SA 3
119 | 264 | 11:34 | 11:36 | 121 | 13777 |  |  | 0:02 | Strip024, Crossline for SA 3
118 | 168 | 11:44 | 11:45 | 119 | 13289 |  |  | 0:01 | Strip025, Crossline for SA 4
117 | 170 | 11:49 | 11:50 | 124 | 12606 |  |  | 0:01 | Strip026, Crossline for SA 4, Flight plan change to Brightangle, due to lack of oxygen
101 | 114 | 11:58 | 11:59 | 130 | 11726 |  |  | 0:01 | Strip027
102 | 294 | 12:02 | 12:03 | 126 | 11681 |  |  | 0:01 | Strip028
103 | 114 | 12:07 | 12:08 | 126 | 11561 |  |  | 0:01 | Strip029
104 | 294 | 12:11 | 12:14 | 124 | 12233 |  |  | 0:03 | Strip030
105 | 114 | 12:17 | 12:20 | 128 | 11994 |  |  | 0:03 | Strip031
106 | 294 | 12:24 | 12:27 | 128 | 11710 |  |  | 0:03 | Strip032
107 | 114 | 12:30 | 12:33 | 122 | 11681 |  |  | 0:03 | Strip033
108 | 294 | 12:36 | 12:40 | 124 | 11513 |  |  | 0:04 | Strip034
109 | 114 | 12:43 | 12:47 | 122 | 11392 |  |  | 0:04 | Strip035
110 | 294 | 12:51 | 12:56 | 130 | 11605 |  |  | 0:05 | Strip036
111 | 114 | 12:59 | 13:05 | 122 | 11609 |  |  | 0:06 | Strip037
112 | 294 | 13:08 | 13:14 | 119 | 11501 |  |  | 0:06 | Strip038
113 | 114 | 13:17 | 13:23 | 121 | 11150 |  |  | 0:06 | Strip039
114 | 294 | 13:27 | 13:33 | 128 | 11012 |  |  | 0:06 | Strip040
115 | 114 | 13:36 | 13:42 | 126 | 10955 |  |  | 0:06 | Strip041
116 | 294 | 13:46 | 13:52 | 119 | 11112 |  |  | 0:06 | Strip042
117 | 114 | 13:55 | 14:01 | 128 | 11000 |  |  | 0:06 | Strip043, entered the beginning of the line at an angle.
148 | 202 | 14:07 | 14:09 | 124 | 10509 |  |  | 0:02 | Strip044 Crossline Exceeded scan angle in the beginning of the line.
149 | 202 | 14:14 | 14:16 | 113 | 10067 |  |  | 0:02 | Strip045 Crossline
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00
0:00

## Sheet3
TOPCON
1