## Errors_For_Corrections_Final
0
NAME | Fixed | Tiles to Remake
Anomaly_1 | X | 13SDE492416 | 13SDE493416 | [6 empty] | Recreated DEM
Anomaly_2 | X | 13SDD499399 | [7 empty] | Adjusted dataset to match
Anomaly_3 | X | 13SED547398 | [7 empty] | Adjusted dataset to match
Anomaly_4 | X | 13SED531377 | 13SED531378 | [6 empty] | Adjusted dataset to match
Anomaly_5 | X | 13SDD486381
Anomaly_7 | X | 13TDE471431 | [7 empty] | Farm road in center of anomaly call, no issue found with LAS file
Anomaly_8 | X | 13SDE484407 | 13SDE486407
Anomaly_9 | X | 13SDE493414 | [7 empty] | Will clean up below Culvert 5 call
Breakline_Residual_1 | X | 13SDE477407 | 13SDE478407
Bridge_Please_Remove_1 | X | 13TDE480431
Bridge_Please_Remove_10 | X | 13SEE511423 | [7 empty] | Changed Surface to remove bridge. Bridge Saddle will appear on the DEM
Bridge_Please_Remove_11 | X | 13SEE516423 | [7 empty] | *No Change to Surface. Bridge is cleaned up. Looks to be the result of a bridge saddle in the DEM
Bridge_Please_Remove_12 | X | 13SEE501420 | [7 empty] | Changed Surface to remove bridge. Bridge Saddle will appear on the DEM
Bridge_Please_Remove_13 | X | 13SDE484422 | [7 empty] | Changed Surface to remove bridge. Bridge Saddle will appear on the DEM
Bridge_Please_Remove_14 | X | 13SDE486422 | [7 empty] | Changed Surface to remove bridge. Bridge Saddle will appear on the DEM
Bridge_Please_Remove_15 | X | 13SDE480422
Bridge_Please_Remove_16 | X | 13SDE495416
Bridge_Please_Remove_17 | X | 13SDE493414 | [7 empty] | Changed Surface to remove bridge. Bridge Saddle will appear on the DEM
Bridge_Please_Remove_18 | X | 13SDE492413 | [7 empty] | Changed Surface to remove bridge. Bridge Saddle will appear on the DEM
Bridge_Please_Remove_19 | X | 13SEE510413
Bridge_Please_Remove_2 | X | 13TEE514431 | [7 empty] | Changed Surface to remove bridge. Bridge Saddle will appear on the DEM
Bridge_Please_Remove_20 | X | 13SDE484402
Bridge_Please_Remove_21 | X | 13SDD496398
Bridge_Please_Remove_22 | X | 13SDD498398
Bridge_Please_Remove_23 | X | 13SDD496398
Bridge_Please_Remove_24 | X | 13SDD496396
Bridge_Please_Remove_25 | X | 13SDD495396
Bridge_Please_Remove_26 | X | 13SDD495396
Bridge_Please_Remove_27 | X | 13SED508390
Bridge_Please_Remove_28 | X | 13SDD499392
Bridge_Please_Remove_29 | X | 13SED501384 | 13SDD499384
Bridge_Please_Remove_3 | X | 13TEE505428
Bridge_Please_Remove_30 | X | 13SDE487407 | 13SDE489407
Bridge_Please_Remove_31 | X | 13TDE477429
Bridge_Please_Remove_32 | X | 13TDE477429
Bridge_Please_Remove_4 | X | 13TDE481428 | [7 empty] | Changed Surface to remove bridge. Bridge Saddle will appear on the DEM
Bridge_Please_Remove_5 | X | 13TDE480428
Bridge_Please_Remove_6 | X | 13TDE478428 | [7 empty] | Changed Surface to remove bridge. Bridge Saddle will appear on the DEM
Bridge_Please_Remove_7 | X | 13SDE477426 | [7 empty] | Structure looks more like a tunnel at ground level. No changes made to DEM
Bridge_Please_Remove_8 | X | 13TDE477428
Bridge_Please_Remove_9 | X | 13SEE501423
Culvert_Replace_Points_1 | X | 13SDE492402 | [7 empty] | Treat this as a bridge feature
Culvert_Replace_Points_3 | X | 13SDD496387 | [7 empty] | Treat this as a bridge feature
Culvert_Replace_Points_4 | X | 13SDE495419 | [7 empty] | Treated this as a culvert Google Earth shows box culvert
Culvert_Replace_Points_5 | X | 13SDE493414 | [7 empty] | Treat this as a bridge feature
Data_Void_1 | X | 13TDE474428 | [7 empty] | LAS file is complete. Remake DEM feature
Earth Removal_1 | X | 13SDE475411 | [7 empty] | Send screen capture when DEM is generated to Pat/Group
Edge_Artifact_Bridge_Removal_1 | X | 13SEE528408 | 13SEE526408
Edge_Mismatch_1 | X | 13SDE498410 | 13SDE498411 | 13SDE496410 | 13SDE496411 |  |  |  |  | Different density datasets come together at this location. Attempted to clean up surface along the tie edge
Edge_Mismatch_10 | X | 13SEE513426 | 13SEE514426
Edge_Mismatch_12 | X | 13SDE483405 | 13SDE484405
Edge_Mismatch_13 | X | 13SEE501411 | 13SEE501413 | 13SDE499411 | 13SDE499413 |  |  |  |  | Different density datasets come together at this location. Attempted to clean up surface along the tie edge
Edge_Mismatch_14 | X | 13SEE507402 | 13SEE508402
Edge_Mismatch_15 | X | 13TDE466428 | 13SDE466426 | 13SDE468426 | 13TDE468428
Edge_Mismatch_16 | X | 13SED511371 | 13SED511369 | 13SED513371 | 13SED513369
Edge_Mismatch_2 | X | 13SDE478401 | 13SDE480401 | [6 empty] | Different density datasets come together at this location. Attempted to clean up surface along the tie edge
Edge_Mismatch_3 | X | 13SDD477390 | 13SDD477389 | [6 empty] | Smoothed out in previous delivery. Different density datasets merged together at this location
Edge_Mismatch_4 | X | 13SDD480384 | 13SDD478384
Edge_Mismatch_5 | X | 13SDD484381 | 13SDD484380 | [6 empty] | Different density datasets come together at this location. Attempted to clean up surface along the tie edge
Edge_Mismatch_6 | X | 13SED529378 | 13SED529377 | 13SED528378 | 13SED528377 | 13SED526378 | 13SED526377 | 13SED525378 | 13SED525377
Edge_Mismatch_7 | X | 13SED531377 | 13SED529377 | [6 empty] | Corrected flight line adjustment
Edge_Mismatch_8 | X | 13SED525381 | 13SED523381 | 13SED525380 | 13SED523380
Edge_Mismatch_9 | X | 13TDE472428 | 13TDE474428 | [6 empty] | Different density datasets come together. Cleaned up problem points along tie edge
Hydroflatten_1 | X | 13TEE514428 | 13TEE514429 | 13TEE513428 | 13SEE514426 | 13SEE513426
106

## Sheet1
13SDD477390
13SDD480384
13SDD484381
13SDD486381
13SDD495396
13SDD496387
13SDD496396
13SDD496398
13SDD498398
13SDD499392
13SDD499399
13SDE475411
13SDE477407
13SDE477426
13SDE478401
13SDE480422
13SDE483405
13SDE484402
13SDE484407
13SDE484422
13SDE486422
13SDE487407
13SDE492402
13SDE492413
13SDE492416
13SDE493414
13SDE495416
13SDE495419
13SDE498410
13SED501384
13SED508390
13SED511371
13SED525381
13SED529378
13SED531377
13SED547398
13SEE501411
13SEE501420
13SEE501423
13SEE507402
13SEE510413
13SEE511423
13SEE513426
13SEE516423
13SEE528408
13TDE466428
13TDE471431
13TDE472428
13TDE474428
13TDE477428
13TDE477429
13TDE478428
13TDE480428
13TDE480431
13TDE481428
13TEE505428
13TEE514428
13TEE514431
13SDD477389
13SDD478384
13SDD484380
13SDD499384
13SDE466426
13SDE478407
13SDE480401
13SDE484405
13SDE486407
13SDE489407
13SDE493416
13SDE498411
13SED511369
13SED523381
13SED529377
13SED531378
13SEE501413
13SEE508402
13SEE514426
13SEE526408
13TEE514429
13SDE468426
13SDE496410
13SDE499411
13SED513371
13SED525380
13SED528378
13TEE513428
13SDE496411
13SDE499413
13SED513369
13SED523380
13SED528377
13TDE468428
13SED526378
13SED526377
13SED525378
13SED525377